## 1 · Structured Abstract
STRUCTURED ABSTRACT · you own this — write it BEFORE you run the study
Owner | Dana S. (example) | [ your name ]
Last updated | 2026-07-14 | [ date ]
Version | v3 | v1
Section | Example — CS1 debugging-prompt study | Your entry
Title | Metacognitive debugging prompts in CS1
Background & context | CS1 students rarely ask for help while debugging, and when they do it is often too late. Reflective prompts might change that.
Objective / research question | Does a "what have you already tried?" prompt change how intro-CS students seek help while debugging?
Methods — Design | Convergent mixed methods: a quasi-experiment across two CS1 sections + follow-up interviews.
Methods — Sample & recruitment | ~120 students across two sections; 12 students interviewed (purposive).
Methods — Measures / data sources | IDE help-request events; 30-min semi-structured interviews.
Methods — Analysis plan (qual / quant / mixed + integration) | Logistic regression on help-request rate + reflexive thematic analysis of interviews, joined in a joint display. Sequence + integration decided now.
Expected contribution (replaces "Results") | A reusable CS1 lab-design guideline about reflective prompts.
Impact if results are POSITIVE | Prompt raises productive help-seeking → ship the guideline + the prompt wording.
Impact if results are NEUTRAL or OPPOSITE | No change in the rate — but interviews explain WHY students route around the prompt (reads as a gate, not an offer): a CS-ed contribution + redesign brief.
Robust to outcome? (Y / N) | Y
Qualitative strand? (Y / N + method) | Y — reflexive thematic analysis
Pre-registered / Registered Report? (link + stage) | osf.io/xxxxx (pre-registered, Stage 1)
How to use this tab: fill column C top-down. If "Impact if results are NEUTRAL or OPPOSITE" is blank, the design is fragile (the flag turns red) — revise the question until a null result still teaches something. Deep guidance: /wiki/project-management/scope

## 2 · Timeline
TIMELINE · plan backward from the deadline; re-plan on a cadence
▼ EXAMPLE — CS1 debugging-prompt study (2-year MS). Build yours in the BLANK template below.
[5 empty] | Year 1 |  |  |  | Year 2
Task / subtask | Owner | Depends-on | Buffer (wks) | Type | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Aim 1 — Setup & IRB
Draft & submit IRB protocol | Dana | — | 2 | milestone | IRB
◆ IRB approved | IRB | protocol | 0 | milestone | ◆
Recruit & consent | Dana | IRB approved | 3 | milestone
Aim 2 — Data collection
Collect IDE logs + interviews | Dana | recruiting | 3 | milestone
▲ Go/no-go after pilot | Team | pilot data | 0 | decision |  |  | ▲
Aim 3 — Analysis
Analysis (qual + quant) + joint display | Dana | data complete | 2 | milestone
Writing & submission
Draft + revise the paper | Dana | analysis | 3 | deadline
◆ Conference deadline | — | draft | 0 | deadline | [7 empty] | ◆
Legend
Aim 1 — setup / IRB
Aim 2 — data collection
Aim 3 — analysis
Writing & submission
◆ ▲ | ◆ = milestone / deliverable ▲ = go/no-go decision · "Buffer (wks)" column = named buffer per phase
▼ BLANK TEMPLATE — fill this in for your project
[5 empty] | Year 1 |  |  |  | Year 2
Task / subtask | Owner | Depends-on | Buffer (wks) | Type | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Aim 1 — Setup & IRB
Aim 2 — Data collection
Aim 3 — Analysis
Writing & submission
Milestones (◆) / decisions (▲)
Legend
Aim 1 — setup / IRB
Aim 2 — data collection
Aim 3 — analysis
Writing & submission
◆ ▲ | ◆ = milestone / deliverable ▲ = go/no-go decision · "Buffer (wks)" column = named buffer per phase

## 3 · Status Tracking
STATUS TRACKING · you own this — update it BEFORE your 1:1
Owner: | [ your name ] | Last updated: | [ date ]
SECTION A · Task board — WIP limit: keep 2–3 tasks in "Doing"
In "Doing" now:
Task | Status | Priority | Definition of Done | Blocker
Reproduce Figure 2 pipeline | Doing | High | Script regenerates the figure from raw CSV in one run | waiting on cleaned data
Code 12 interview transcripts | Doing | High | All transcripts first-cycle coded in the codebook
Draft methods section | Backlog | Med | Shared with advisor for review
SECTION B · Weekly + 1:1 log — write 4 lines every week (Tried / Learned / Decided / Next)
Date | Week / Sprint # | One-line status | Did (since last) | Blockers | Next actions (owner + due) | Advisor decisions
2026-07-10 | Wk 3 | On track | Coded 8 transcripts; drafted methods | Recruitment slow (6/12) | Email dept listserv by 7/17 (Dana) | Extend recruiting 2 wks; start analysis on the pilot set
Close the loop: send a 3–6 bullet decision summary within ~24h of each 1:1. Deep guidance: /wiki/project-management/status-tracking